## Implementation Tasks
# | Phase | Task | Sub-Tasks / Details | Layer | Key Files | Prompt Hint (for AI) | Status
1 | Phase 1: Setup | Backend scaffolding | Create FastAPI project structure, folder hierarchy, requirements.txt, .env.example with DB_CONNECTION_STRING, JWT_SECRET, AZURE_BLOB_CONNECTION_STRING, AZURE_BLOB_CONTAINER | Backend | backend/app/main.py, backend/requirements.txt, backend/.env.example | Create a FastAPI backend project with folder structure: app/core/, app/models/, app/schemas/, app/api/v1/, app/services/. Include .env.example with all config vars. Use pydantic-settings for config. | To Do
2 | Phase 1: Setup | DB connection setup | SQLAlchemy engine config for SQL Server using pyodbc. Connection string from .env. Async session maker. Dev: local SQL Server. Prod: Azure SQL Server. | Backend | backend/app/core/config.py, backend/app/core/dependencies.py | Set up SQLAlchemy with SQL Server using mssql+pyodbc. Load connection string from .env. Create async engine, sessionmaker, and get_db dependency. Support both local and Azure SQL Server. | To Do
3 | Phase 1: Setup | Alembic setup | Initialize Alembic for SQL Server. Configure env.py to read DB URL from .env. | Backend | backend/alembic/, backend/alembic.ini, backend/alembic/env.py | Initialize Alembic in the backend project. Configure alembic.ini and env.py to use SQL Server connection string from .env. Set up for auto-generating migrations from SQLAlchemy models. | To Do
4 | Phase 1: Setup | Frontend scaffolding | ng new with Angular 19 standalone components. Install Angular Material. Set up routing, environments, proxy config for API. | Frontend | frontend/src/app/app.config.ts, frontend/src/app/app.routes.ts, frontend/angular.json | Create Angular 19 project with standalone components (no NgModules). Install Angular Material. Set up app.routes.ts with lazy-loaded routes. Configure proxy.conf.json to forward /api to FastAPI backend. | To Do
5 | Phase 1: Setup | CORS configuration | Configure FastAPI CORS middleware to allow Angular dev server (localhost:4200). | Backend | backend/app/main.py | Add CORS middleware to FastAPI main.py allowing origins from .env (default localhost:4200). Allow credentials, all methods, all headers. | To Do
6 | Phase 2: Models & Auth | SQLAlchemy models - Company, User, UserRoleMap | Company model with optional SMTP fields. User model (password varchar 255). UserRoleMap (userId, roleId, companyId, isDefault). | Backend | backend/app/models/company.py, backend/app/models/user.py | Create SQLAlchemy models for Company (with nullable MailFrom, MailPassword, SMTP, PortNo), User (userPassword varchar 255 for bcrypt), and UserRoleMap (userId, roleId, companyId, isDefault bit). Add relationships. | To Do
7 | Phase 2: Models & Auth | SQLAlchemy models - Role, Menu, RoleMenuMap | Role model with IsSuperAdmin. MenuMaster with self-referencing parentMenuId for unlimited nesting. RoleMenuMap with CanAdd/CanRead/CanEdit/CanDelete. | Backend | backend/app/models/role.py, backend/app/models/menu.py, backend/app/models/role_menu_map.py | Create SQLAlchemy models for Role (with IsSuperAdmin bit), MenuMaster (self-referencing FK parentMenuId for tree structure, menuOrder for sorting), RoleMenuMap (roleId, menuId, CanAdd, CanRead, CanEdit, CanDelete). Add parent-children relationship on MenuMaster. | To Do
8 | Phase 2: Models & Auth | SQLAlchemy models - Item, Delivery, Classification, ContactType | ItemGrade, ItemName, ItemLength, ItemSize, DeliveryTerm, DeliveryMode, CustomerClassification, ContactType, CostPointMaster. | Backend | backend/app/models/item.py, backend/app/models/delivery.py, backend/app/models/customer_classification.py, backend/app/models/contact_type.py, backend/app/models/cost_point.py | Create SQLAlchemy models for: ItemGrade, ItemName (FK to grade), ItemLength (FK to item), ItemSize (FK to item, corrected: itemSize varchar 50), DeliveryTerm, DeliveryMode, CustomerClassification, ContactType, CostPointMaster (isPrimary, isTax). All have companyId, isActive, audit fields. | To Do
9 | Phase 2: Models & Auth | SQLAlchemy models - Customer, Enquiry, Quotation, Asset | CustomerMaster, CustomerContacts (FK), CustomerSite (FK). CustomerEnquiry + Details + Costing (with versionNo). QuotSummary (with versionNo, parentQuotId) + Details + T&C. TermsNConditionMaster, RawMaterialCost. Asset. | Backend | backend/app/models/customer.py, backend/app/models/enquiry.py, backend/app/models/quotation.py, backend/app/models/terms_condition.py, backend/app/models/raw_material_cost.py, backend/app/models/asset.py | Create SQLAlchemy models for: CustomerMaster, CustomerContacts (FK customerId), CustomerSite (FK customerId). CustomerEnquiry, CustomerEnquiryDetails (FK enqid), CustomerEnquiryCosting (FK enqid + enqdtlid, add versionNo int default 1). QuotSummary (add versionNo, parentQuotId nullable self-FK), QuotDetails (FK quotId), QuotTermsNConditions (FK quotId). TermsNConditionMaster. RawMaterialCost. Asset (FK enqid, quotId). | To Do
10 | Phase 2: Models & Auth | Alembic initial migration | Generate migration from all 25 models. Run migration to create tables. | Backend | backend/alembic/versions/ | Generate Alembic migration: alembic revision --autogenerate -m "initial_schema". Review and run: alembic upgrade head. Verify all 25 tables created in SQL Server. | To Do
11 | Phase 2: Models & Auth | JWT auth - security module | Password hashing with bcrypt. JWT token creation (access + refresh). Token verification. Token payload: { user_id, company_id, role_id, is_super_admin }. | Backend | backend/app/core/security.py | Create security.py with: bcrypt password hashing (hash_password, verify_password), JWT token creation (create_access_token, create_refresh_token) with payload { user_id, company_id, role_id, is_super_admin, exp }. Token verification. Use python-jose and passlib[bcrypt]. | To Do
12 | Phase 2: Models & Auth | Auth API endpoints | POST /login (validate credentials, return companies list + temp token). POST /select-company (issue full JWT). POST /switch-company (re-issue JWT). POST /refresh-token. | Backend | backend/app/api/v1/auth.py, backend/app/services/auth_service.py | Create auth endpoints: POST /api/v1/auth/login (validate user credentials, return list of user companies from UserRoleMap + temporary token), POST /api/v1/auth/select-company (given temp token + companyId, issue full JWT), POST /api/v1/auth/switch-company (given current JWT + new companyId, re-issue JWT), POST /api/v1/auth/refresh (refresh token flow). | To Do
13 | Phase 2: Models & Auth | Auth dependencies & middleware | get_current_user dependency (extract from JWT). get_active_company. Permission checker dependency (check RoleMenuMap for menu + action). | Backend | backend/app/core/dependencies.py | Create FastAPI dependencies: get_current_user (decode JWT, return user with active company_id and role_id), get_active_company (extract companyId from JWT for query filtering), require_permission(menu_name, action) dependency factory that checks RoleMenuMap for the user role and returns 403 if not allowed. | To Do
14 | Phase 2: Models & Auth | Frontend - Login page | Login form (username, password). On success: if single company auto-proceed, if multiple show company picker dropdown. Store JWT tokens. Redirect to dashboard. | Frontend | frontend/src/app/features/auth/login/ | Create Angular login component with reactive form (username, password). Call POST /api/v1/auth/login. If response has multiple companies, show a dropdown to select company, then call POST /select-company. Store access and refresh tokens in localStorage. Redirect to /dashboard. | To Do
15 | Phase 2: Models & Auth | Frontend - Auth service & interceptor | AuthService (login, selectCompany, switchCompany, logout, isAuthenticated). TokenService (store/get/remove tokens). HTTP interceptor (attach Bearer token, handle 401 -> redirect to login). AuthGuard. | Frontend | frontend/src/app/core/auth/ | Create AuthService (login, selectCompany, switchCompany, logout, isAuthenticated, getCurrentUser), TokenService (getAccessToken, getRefreshToken, setTokens, clearTokens). HTTP interceptor to add Authorization header, catch 401 -> logout and redirect. AuthGuard (canActivate checks isAuthenticated). | To Do
16 | Phase 3: Company/User/Role | Company CRUD - Backend API | CRUD endpoints for Company. Super Admin only. Includes optional SMTP/email config fields. | Backend | backend/app/api/v1/company.py, backend/app/schemas/company.py | Create Company Pydantic schemas (Create, Update, Response) with all fields including nullable SMTP fields. Create CRUD endpoints: GET /api/v1/companies, GET /{id}, POST, PUT /{id}, DELETE /{id} (soft delete). Protect with Super Admin check. | To Do
17 | Phase 3: Company/User/Role | Company CRUD - Frontend | Company list page with mat-table. Add/Edit form dialog with all fields including optional SMTP configuration section. | Frontend | frontend/src/app/features/company/ | Create company-list component with Angular Material table (search, pagination). Add/Edit company dialog with reactive form. Include SMTP settings section (MailFrom, MailPassword, SMTP host, PortNo) marked as optional. Only visible to Super Admin. | To Do
18 | Phase 3: Company/User/Role | Role CRUD - Backend + Frontend | Role CRUD endpoints (company-scoped). Angular list + add/edit dialog. | Full Stack | backend/app/api/v1/roles.py, frontend/src/app/features/roles/ | Backend: Create Role schemas and CRUD endpoints filtered by companyId. Frontend: Role list page (mat-table) + add/edit dialog (roleName, isSuperAdmin checkbox). Company-scoped. | To Do
19 | Phase 3: Company/User/Role | Menu Master CRUD - Backend | CRUD endpoints for MenuMaster. GET /menus/tree returns recursive tree JSON. parentMenuId for nesting. | Backend | backend/app/api/v1/menus.py, backend/app/services/menu_service.py | Create MenuMaster CRUD endpoints. Key endpoint: GET /api/v1/menus/tree that builds recursive tree from flat menu records (group by parentMenuId, sort by menuOrder). Return nested JSON: [{menuId, menuName, menuOrder, children: [...]}]. Service: build_menu_tree(company_id) method. | To Do
20 | Phase 3: Company/User/Role | Menu Master CRUD - Frontend | Menu management page. Display tree using mat-tree. Add/edit menu items. Drag-drop reorder. Set parent menu. | Frontend | frontend/src/app/features/masters/menu/ | Create menu management component using Angular Material mat-tree to display nested menus. Add/edit dialog (menuName, parentMenuId dropdown, menuOrder). Support drag-drop reorder to change menuOrder. Show tree hierarchy. | To Do
21 | Phase 3: Company/User/Role | Role-Menu Mapping - Backend | GET /role-menu-map/{roleId} returns current permissions. POST /role-menu-map/{roleId} saves permissions as flat array. | Backend | backend/app/api/v1/roles.py (or separate role_menu_map.py) | Create endpoints: GET /api/v1/role-menu-map/{roleId} returns list of {menuId, menuName, canAdd, canRead, canEdit, canDelete} for all menus (with current permissions for this role). POST /api/v1/role-menu-map/{roleId} accepts array of {menuId, canAdd, canRead, canEdit, canDelete} and bulk upserts. | To Do
22 | Phase 3: Company/User/Role | Role-Menu Mapping - Frontend (Tree with Checkboxes) | Tree view using mat-tree. Each node shows menu name + 4 checkboxes (CanAdd, CanRead, CanEdit, CanDelete). Parent checkbox toggles all children. Select role dropdown at top. | Frontend | frontend/src/app/features/roles/role-menu-mapping/ | Create role-menu-mapping component. Top: role dropdown. Below: mat-tree displaying menu hierarchy. Each tree node has 4 checkboxes (CanAdd, CanRead, CanEdit, CanDelete). Checking a parent toggles all descendants. Unchecking a child unchecks the parent if all children are unchecked. Save button sends flat array to backend. | To Do
23 | Phase 3: Company/User/Role | User CRUD - Backend | User CRUD endpoints. Include UserRoleMap management (assign user to companies with roles). | Backend | backend/app/api/v1/users.py, backend/app/services/user_service.py | Create User CRUD endpoints. On create: hash password with bcrypt. Include sub-resource: POST /users/{id}/role-mappings to assign user to companies with roles (creates UserRoleMap entries). GET /users/{id}/role-mappings returns list of {companyId, companyName, roleId, roleName, isDefault}. | To Do
24 | Phase 3: Company/User/Role | User CRUD - Frontend | User list page. User form with basic info + company-role mapping section (add multiple company+role pairs). | Frontend | frontend/src/app/features/users/ | Create user-list component (mat-table with search). User form: basic fields (name, code, email, phone, login, password, reportTo dropdown). Below: company-role mapping section - add rows with company dropdown + role dropdown + isDefault checkbox. Save creates user + role mappings. | To Do
25 | Phase 3: Company/User/Role | Dynamic sidebar menu | Fetch user-permitted menu tree (only nodes with CanRead=true for user role). Render as recursive mat-tree sidebar. Re-fetch on company switch. | Frontend | frontend/src/app/shared/components/dynamic-menu/, frontend/src/app/core/services/menu.service.ts | Create MenuService that calls GET /api/v1/menus/user-tree (backend filters by role permissions, returns only CanRead=true nodes as tree). Create dynamic-menu component using recursive mat-tree in sidenav. Each leaf node links to a route. Re-fetch menu tree when company changes. | To Do
26 | Phase 3: Company/User/Role | Company Switcher | Dropdown in header showing user companies. On switch: call switch-company API, update JWT, reload menu + current page data. | Frontend | frontend/src/app/shared/components/company-switcher/, frontend/src/app/core/services/company-context.service.ts | Create CompanyContextService that tracks active company, provides switchCompany() method. Create company-switcher component (mat-select in toolbar). On switch: call POST /auth/switch-company, store new JWT, emit companyChanged event. All data-fetching components subscribe to companyChanged and reload. | To Do
27 | Phase 3: Company/User/Role | Permission directive | *hasPermission structural directive that shows/hides elements based on user role permissions for a specific menu + action. | Frontend | frontend/src/app/shared/directives/has-permission.directive.ts | Create *hasPermission structural directive. Usage: *hasPermission="'ItemGrade:CanEdit'". Directive checks the cached RoleMenuMap permissions (from MenuService) for the current role. If permission is false, remove element from DOM. Also create PermissionGuard for route-level protection. | To Do
28 | Phase 4: Masters | Generic master CRUD pattern - Backend | Create reusable pattern for simple master tables: schema, CRUD endpoints, company-scoped, soft delete, permission-checked. | Backend | backend/app/api/v1/masters.py | Create a generic CRUD pattern for master tables. Each master needs: Pydantic schemas (Create, Update, Response), router with GET list (filtered by companyId, isActive), GET by id, POST, PUT, soft DELETE. Apply require_permission dependency. Start with ItemGrade as the template, then replicate for all 11 masters. | To Do
29 | Phase 4: Masters | Generic master CRUD pattern - Frontend | Create reusable pattern for simple masters: list page (mat-table + search + pagination) + add/edit dialog + delete confirmation. | Frontend | frontend/src/app/features/masters/ | Create reusable data-table component (mat-table with search, sort, pagination, action buttons). Create confirm-dialog component. For each master: list component using data-table + add/edit dialog with reactive form. Start with item-grade as template. Fields vary per master but pattern is same. | To Do
30 | Phase 4: Masters | Item Grade CRUD | Backend API + Frontend UI for ItemGrade master. | Full Stack | backend/app/api/v1/masters.py, frontend/src/app/features/masters/item-grade/ | Implement ItemGrade: Backend schema + CRUD endpoints at /api/v1/masters/item-grades. Frontend: item-grade-list (mat-table) + item-grade-dialog (itemGradeName field). This serves as the template for all other masters. | To Do
31 | Phase 4: Masters | Item Name CRUD | ItemName with fields: itemGradeName, itemName, itemDia, itemLength, erpItemCode, erpName. Linked to ItemGrade. | Full Stack | frontend/src/app/features/masters/item-name/ | Implement ItemName CRUD. Form has: itemGradeName (dropdown from ItemGrade), itemName, itemDia, itemLength, erpItemCode, erpName. Backend: /api/v1/masters/item-names. | To Do
32 | Phase 4: Masters | Item Length & Item Size CRUD | ItemLength (FK itemId, itemLength). ItemSize (FK itemId, itemSize). Both linked to ItemName. | Full Stack | frontend/src/app/features/masters/item-length/, frontend/src/app/features/masters/item-size/ | Implement ItemLength CRUD (itemId dropdown from ItemName, itemLength field) and ItemSize CRUD (itemId dropdown, itemSize field). Backend endpoints at /api/v1/masters/item-lengths and /api/v1/masters/item-sizes. | To Do
33 | Phase 4: Masters | Delivery Term & Delivery Mode CRUD | Simple single-field masters: deliveryTerm, deliveryMode. | Full Stack | frontend/src/app/features/masters/delivery-term/, frontend/src/app/features/masters/delivery-mode/ | Implement DeliveryTerm CRUD (deliveryTerm field) and DeliveryMode CRUD (deliveryMode field). Simple single-field master pattern. Backend: /api/v1/masters/delivery-terms and /delivery-modes. | To Do
34 | Phase 4: Masters | Contact Type & Customer Classification CRUD | ContactType (contactType). CustomerClassification (classificationName). | Full Stack | frontend/src/app/features/masters/contact-type/, frontend/src/app/features/masters/customer-classification/ | Implement ContactType CRUD (contactType field) and CustomerClassification CRUD (classificationName field). Simple single-field masters. | To Do
35 | Phase 4: Masters | Cost Point Master CRUD | CostPointMaster with costPointName, isPrimary (bit), isTax (bit). | Full Stack | frontend/src/app/features/masters/cost-point/ | Implement CostPointMaster CRUD. Form: costPointName, isPrimary checkbox, isTax checkbox. Backend: /api/v1/masters/cost-points. | To Do
36 | Phase 4: Masters | Terms & Conditions Master CRUD | TermsNConditionMaster with tncName, tncDescription (varchar 500). | Full Stack | frontend/src/app/features/masters/terms-condition/ | Implement TermsNConditionMaster CRUD. Form: tncName, tncDescription (textarea). Backend: /api/v1/masters/terms-conditions. | To Do
37 | Phase 4: Masters | Raw Material Cost CRUD | RawMaterialCost with dia, tpcost (money), effectedFrom (datetime). | Full Stack | frontend/src/app/features/masters/raw-material-cost/ | Implement RawMaterialCost CRUD. Form: dia (text), tpcost (currency input), effectedFrom (date picker). Backend: /api/v1/masters/raw-material-costs. No lastupdateon/lastupdateby on this table. | To Do
38 | Phase 5: Customers | Customer Master - Backend API | CRUD endpoints for CustomerMaster. Include related contacts and sites in GET response. Search/filter by name, code, classification. | Backend | backend/app/api/v1/customers.py, backend/app/schemas/customer.py | Create CustomerMaster schemas and CRUD endpoints. GET /customers supports search by customerName, customerCode, classificationName. GET /customers/{id} includes nested contacts and sites. POST/PUT handle customer basic info only. Separate sub-resource endpoints for contacts and sites. | To Do
39 | Phase 5: Customers | Customer Contacts - Backend API | CRUD endpoints for CustomerContacts as sub-resource of customer. Multiple contacts per customer. | Backend | backend/app/api/v1/customers.py | Create CustomerContacts endpoints: GET /customers/{customerId}/contacts, POST /customers/{customerId}/contacts, PUT /customers/{customerId}/contacts/{contactId}, DELETE (soft). Schema includes contactType, contactPersonName, designation, phones, emails, address, state, dist, birthday, anniversary, office contacts. | To Do
40 | Phase 5: Customers | Customer Sites - Backend API | CRUD endpoints for CustomerSite as sub-resource. Multiple delivery sites per customer with up to 3 contact persons each. | Backend | backend/app/api/v1/customers.py | Create CustomerSite endpoints: GET /customers/{customerId}/sites, POST, PUT, soft DELETE. Schema includes siteAddressCode, addressLine, state, dist, PIN, and 3 sets of contactPerson/Phone/Email fields. | To Do
41 | Phase 5: Customers | Customer Management - Frontend | Customer list page (mat-table, search, filter by classification). Customer form with 3 tabs: Basic Info, Contacts, Sites. Each tab manages its own sub-table. | Frontend | frontend/src/app/features/customers/ | Create customer-list (mat-table, search, classification filter). Create customer-form with 3 mat-tabs: Tab 1 (Basic Info: classificationName dropdown, customerCode, customerName, GSTN, PAN, siteId). Tab 2 (Contacts: mat-table with add/edit/delete inline or dialog). Tab 3 (Sites: mat-table with add/edit/delete). Save each tab independently. | To Do
42 | Phase 6: Enquiries | Enquiry CRUD - Backend API | CRUD endpoints for CustomerEnquiry. On customer select, return their contacts and sites. Include nested details. | Backend | backend/app/api/v1/enquiries.py, backend/app/services/enquiry_service.py | Create CustomerEnquiry CRUD endpoints. GET /enquiries (list with filters: customer, date range). GET /enquiries/{id} includes nested EnquiryDetails and latest EnquiryCosting. POST creates header only. Helper: GET /customers/{id}/summary returns contacts + sites for dropdown population. | To Do
43 | Phase 6: Enquiries | Enquiry Details CRUD - Backend API | CRUD for CustomerEnquiryDetails as sub-resource of enquiry. Line items: item, grade, dia, length, unit. | Backend | backend/app/api/v1/enquiries.py | Create EnquiryDetails endpoints: GET /enquiries/{enqId}/details, POST (add line item), PUT /{dtlId}, soft DELETE. Each detail has: itemid (FK), itemGradeName, itemDia, itemLength, itemUnit. | To Do
44 | Phase 6: Enquiries | Enquiry Costing CRUD - Backend API (Versioned) | CRUD for CustomerEnquiryCosting. 20+ cost heads per line item. Version control: create new version duplicates with versionNo+1. Auto-fill TP from RawMaterialCost. | Backend | backend/app/api/v1/enquiries.py, backend/app/services/costing_service.py | Create EnquiryCosting endpoints. GET /enquiries/{enqId}/costing?version=latest returns costing for all line items. POST /enquiries/{enqId}/costing creates/updates costing per detail. POST /enquiries/{enqId}/costing/new-version duplicates latest version with versionNo+1. GET /enquiries/{enqId}/costing/versions lists all versions. Auto-fill TPWGST from RawMaterialCost by matching dia. Calculate basicRate, GST (18%), EXFORPrice. | To Do
45 | Phase 6: Enquiries | Enquiry Management - Frontend | Enquiry list. Enquiry form (customer selector, auto-populate contacts/sites). Enquiry details (editable line items table). Enquiry costing (cost breakdown grid with version controls). | Frontend | frontend/src/app/features/enquiries/ | Create enquiry-list (mat-table, filters). Enquiry-form: customer dropdown (on select, populate contact and site dropdowns), enqDate picker, enqMode, description, validityDays. Enquiry-details: editable mat-table for line items (item dropdown, grade, dia, length, unit, add/remove rows). Enquiry-costing: grid showing all 20+ cost heads per line item, auto-calculate totals. Version dropdown to switch versions. "Create New Version" button. Previous versions read-only. | To Do
46 | Phase 7: Quotations | Quotation CRUD - Backend API (Versioned) | CRUD for QuotSummary with versioning. Link to enquiry, customer, site, contact. Revision creates new row with versionNo+1, parentQuotId. | Backend | backend/app/api/v1/quotations.py, backend/app/services/quotation_service.py, backend/app/services/versioning_service.py | Create QuotSummary CRUD endpoints. GET /quotations (list, show latest version per parentQuotId group). GET /{id} with nested details + T&C. POST creates quotation linked to enquiry. POST /quotations/{id}/revise creates new row with versionNo+1, parentQuotId=original, quotNo format QUOT-XXX-R{n}. GET /quotations/{id}/versions lists all versions. Approval: PUT /quotations/{id}/approve sets approvedby, approvedon (only latest version). | To Do
47 | Phase 7: Quotations | Quotation Details CRUD - Backend | Line items for quotation: grade, dia, length, unit, quantity, basicRate, IGST, CGST, SGST, totAmount, totRate. | Backend | backend/app/api/v1/quotations.py | Create QuotDetails endpoints as sub-resource of quotation. GET /quotations/{quotId}/details, POST, PUT, soft DELETE. Fields: itemGradeName, itemDia, itemLength, itemUnit, quantity, basicRate, IGST, CGST, SGST, totAmount (calculated), totRate (calculated). | To Do
48 | Phase 7: Quotations | Quotation T&C - Backend | Terms & Conditions per quotation. Pull defaults from TermsNConditionMaster, allow per-quotation edit. | Backend | backend/app/api/v1/quotations.py | Create QuotTermsNConditions endpoints. GET /quotations/{quotId}/terms. POST /quotations/{quotId}/terms/from-master copies all active T&C from TermsNConditionMaster to this quotation. PUT /{tncId} allows editing per-quotation. Soft DELETE. | To Do
49 | Phase 7: Quotations | Quotation Management - Frontend | Quotation list (latest versions). Quotation form with customer/enquiry linking. Details table. T&C editor. Version history panel. | Frontend | frontend/src/app/features/quotations/ | Create quotation-list (mat-table showing latest version per quotation, filters). Quotation-form: link to enquiry (dropdown, auto-fills customer/site/contact), quotDate, subject, deliveryTerm/Mode dropdowns, refQuotNo, remarks, CustomerPONo/Date. Quotation-details: editable table (grade, dia, length, qty, rates, GST split, totals). Quotation-tnc: list with add from master button + inline edit. Version-history: side panel listing all versions, click to view (read-only for old versions). "Revise Quotation" button. | To Do
50 | Phase 7: Quotations | Quotation Print/PDF | Formatted printable quotation view for a specific version. Include header, details table, T&C, footer. | Frontend | frontend/src/app/features/quotations/quotation-print/ | Create quotation-print component that renders a formatted quotation for a specific version. Include: company header, quotation details (quotNo, date, customer, site, contact), line items table with totals, T&C section. Use @media print CSS. Add "Print" button that triggers window.print(). Optionally generate PDF using jsPDF or similar. | To Do
51 | Phase 8: Assets & Email | Azure Blob Service | Service for uploading, downloading, and deleting files from Azure Blob Storage. Connection from .env. | Backend | backend/app/services/azure_blob_service.py | Create AzureBlobService using azure-storage-blob SDK. Methods: upload_file(file, container, blob_name), download_file(blob_name), delete_file(blob_name), generate_sas_url(blob_name). Connection string from .env AZURE_BLOB_CONNECTION_STRING. Container from AZURE_BLOB_CONTAINER. | To Do
52 | Phase 8: Assets & Email | Asset CRUD - Backend + Frontend | Upload files linked to enquiry or quotation. List assets. Download. Soft delete. | Full Stack | backend/app/api/v1/assets.py, frontend/src/app/features/assets/ | Backend: POST /api/v1/assets/upload (multipart file + enqid/quotId). GET /assets?enqid=X or ?quotId=X. GET /assets/{id}/download (returns SAS URL or streams file). Soft DELETE. Frontend: asset-upload component (drag-drop or file picker), asset-list component (table with download/delete actions). Integrate into enquiry and quotation detail pages. | To Do
53 | Phase 8: Assets & Email | Email Configuration - Super Admin UI | Company edit form: SMTP settings section (host, port, MailFrom, MailPassword). All optional. If not set, email features hidden. | Frontend | frontend/src/app/features/company/ (update existing) | Update company edit form to include an "Email Configuration" section: SMTP Host, Port, MailFrom (From email address), MailPassword (password input). All fields optional. Add a "Test Connection" button that calls backend to verify SMTP settings. If SMTP not configured for a company, hide all email-related buttons across the app. | To Do
54 | Phase 8: Assets & Email | Mail Template Management | Super Admin can create/edit HTML email templates per company. Templates used when sending quotation emails. | Full Stack | backend/app/api/v1/email.py, frontend/src/app/features/company/ (or dedicated) | Create a simple MailTemplate model (or use a config table) storing template name + HTML body per company. Backend CRUD for templates. Frontend: template editor (textarea or basic rich text) in Super Admin panel. Default template provided. Template supports placeholders like {{customerName}}, {{quotNo}}, {{quotDate}}. | To Do
55 | Phase 8: Assets & Email | Send Quotation Email - Backend + Frontend | Send quotation PDF to customer contact email. From = company MailFrom. To = selected contact email. Uses company SMTP config. | Full Stack | backend/app/services/email_service.py, backend/app/api/v1/email.py | Backend: EmailService that loads company SMTP config, constructs email (From=company MailFrom, To=contact email, subject from template, body from template with placeholders filled, attach quotation PDF). POST /api/v1/email/send-quotation {quotId, contactId, templateId}. Frontend: "Send Email" button on quotation page, shows dialog to confirm recipient (pre-filled from selected contact), select template, send. Button hidden if company SMTP not configured. | To Do